## Test Cases
OpenCart E-Commerce – Manual Test Case Document
TC ID | Module | Test Scenario | Test Case Description | Pre-conditions | Test Steps | Expected Result | Actual Result | Status | Priority | Test Type | Remarks
▶ User Registration
TC_REG_001 | User Registration | Verify successful registration with valid data | New user registers with all mandatory fields filled | User is on Registration page | 1. Navigate to opencart demo 2. Click 'My Account' > 'Register' 3. Enter First Name, Last Name 4. Enter valid Email 5. Enter Password (min 4 chars) 6. Agree to Privacy Policy 7. Click 'Continue' | User is registered and redirected to Account Success page |  | Pass | High | Functional
TC_REG_002 | User Registration | Verify registration fails with existing email | System rejects duplicate email registration | An account already exists with test email | 1. Go to Register page 2. Enter already-registered email 3. Fill other valid fields 4. Click 'Continue' | Error message: 'Warning: E-Mail Address is already registered!' |  | Pass | High | Negative
TC_REG_003 | User Registration | Verify mandatory field validation | System shows errors when mandatory fields are empty | User is on Registration page | 1. Go to Register page 2. Leave all fields blank 3. Click 'Continue' | Validation errors displayed for all mandatory fields |  | Pass | Medium | Negative
TC_REG_004 | User Registration | Verify password mismatch validation | System rejects when Password ≠ Confirm Password | User is on Registration page | 1. Enter valid details 2. Enter different values in Password & Confirm Password 3. Click 'Continue' | Error: 'Password confirmation does not match password!' |  | Pass | Medium | Negative
▶ Login
TC_LOG_001 | Login | Verify login with valid credentials | Registered user logs in successfully | User has a registered account | 1. Click 'My Account' > 'Login' 2. Enter valid Email & Password 3. Click 'Login' | User is redirected to My Account dashboard |  | Pass | High | Functional
TC_LOG_002 | Login | Verify login with invalid password | System rejects wrong password | User is on Login page | 1. Enter valid email 2. Enter incorrect password 3. Click 'Login' | Warning: 'No match for E-Mail Address and/or Password' |  | Pass | High | Negative
TC_LOG_003 | Login | Verify login with blank credentials | System shows validation on empty login form | User is on Login page | 1. Leave Email and Password blank 2. Click 'Login' | Validation errors shown for both fields |  | Pass | Medium | Negative
TC_LOG_004 | Login | Verify 'Forgot Password' functionality | User receives reset email on valid registered email | User has a registered account | 1. Click 'Forgotten Password' 2. Enter registered email 3. Click 'Continue' | Success message: 'An email with a confirmation link has been sent' |  | Pass | Medium | Functional
▶ Search
TC_SRC_001 | Search | Verify search with valid product keyword | Search returns relevant product results | User is on Home page | 1. Enter 'MacBook' in search bar 2. Click Search icon | Products containing 'MacBook' are displayed |  | Pass | High | Functional
TC_SRC_002 | Search | Verify search with invalid/random keyword | Search returns no results message | User is on Home page | 1. Enter 'xyzabc123' in search bar 2. Click Search icon | 'There is no product that matches the search criteria' displayed |  | Pass | Medium | Negative
TC_SRC_003 | Search | Verify search with empty input | System handles blank search gracefully | User is on Home page | 1. Leave search bar empty 2. Click Search icon | Message: 'Search criteria does not match' or results page shown |  | Pass | Low | Negative
▶ Shopping Cart
TC_CART_001 | Shopping Cart | Verify adding a product to cart | Product is added to cart successfully | User is on any Product page | 1. Navigate to a product (e.g. iPhone) 2. Click 'Add to Cart' | Success message: 'Success: You have added [Product] to your shopping cart!' |  | Pass | High | Functional
TC_CART_002 | Shopping Cart | Verify updating product quantity in cart | Cart quantity updates correctly | At least one product is in cart | 1. Go to Shopping Cart 2. Change quantity to 3 3. Click 'Update' | Cart quantity and total price update correctly |  | Pass | High | Functional
TC_CART_003 | Shopping Cart | Verify removing a product from cart | Product is removed from cart | At least one product is in cart | 1. Go to Shopping Cart 2. Click 'Remove' (X icon) next to product | Product removed; cart shows 'Your shopping cart is empty!' |  | Pass | Medium | Functional
TC_CART_004 | Shopping Cart | Verify cart persists after logout and login | Cart items retained across sessions | User logged in with items in cart | 1. Add product to cart 2. Logout 3. Login again 4. Check cart | Previously added products still present in cart |  | Blocked | Low | Functional | Needs session testing
▶ Checkout
TC_CHK_001 | Checkout | Verify checkout as registered user | Logged-in user completes checkout successfully | User logged in; cart has items | 1. Go to Cart > Checkout 2. Confirm Billing Details 3. Choose shipping method 4. Choose payment (COD) 5. Confirm Order | Order placed; redirected to Order Confirmation page with Order ID |  | Pass | High | Functional
TC_CHK_002 | Checkout | Verify checkout as guest user | Guest user can checkout without registration | Cart has items; user not logged in | 1. Go to Cart > Checkout 2. Select 'Guest Checkout' 3. Fill all required fields 4. Complete order | Order placed successfully as guest |  | Pass | High | Functional
TC_CHK_003 | Checkout | Verify checkout with empty cart | System prevents checkout with no items | Cart is empty | 1. Navigate directly to Checkout URL with empty cart | Redirected back to cart page with empty cart message |  | Pass | Medium | Negative
▶ Product Page
TC_PRD_001 | Product Page | Verify product details are displayed correctly | Product name, price, description visible | User is on any product listing | 1. Click on any product 2. Observe product detail page | Product name, images, price, description, Add to Cart button all visible |  | Pass | High | Functional
TC_PRD_002 | Product Page | Verify product image zoom functionality | Image zooms on hover/click | User is on Product Detail page | 1. Hover over product image | Image zooms in and shows enlarged view |  | Fail | Low | UI | Bug: zoom not working on Chrome v120
TC_PRD_003 | Product Page | Verify 'Write a Review' functionality | User can submit a product review | User logged in; on Product page | 1. Click 'Write a Review' 2. Enter Name, Review text, Rating 3. Click 'Continue' | Review submitted successfully; confirmation message shown |  | Pass | Medium | Functional
▶ Navigation
TC_UI_001 | Navigation | Verify all top navigation links work | Navigation links redirect to correct pages | User is on Home page | 1. Click each top-nav link (Desktops, Laptops, etc.) 2. Observe page loaded | Each link navigates to its corresponding category page |  | Pass | High | UI
TC_UI_002 | Navigation | Verify footer links are functional | All footer links navigate correctly | User is on any page | 1. Scroll to footer 2. Click each link (About Us, Contact, etc.) | All footer links open the correct pages |  | Pass | Low | UI
TC_UI_003 | Navigation | Verify website logo redirects to Home | Logo click returns user to Home page | User is on any inner page | 1. Click the OpenCart logo in header | User is redirected to Home page |  | Pass | Medium | UI
Summary
Total TCs | 24 | Passed | 22 | Failed | 1 | Blocked | 1 | Pass % | 70.9677

## Bug Report
OpenCart – Bug Report Log
Bug ID | TC Ref | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Reporter
BUG_001 | TC_PRD_002 | Product Page | Product image zoom not working on Chrome v120 | 1. Open any product page on Chrome v120 2. Hover over product image | Image should zoom in on hover | No zoom effect; image remains static | Minor | Low | Open | Tester
BUG_002 | TC_REG_002 | User Registration | No rate limiting on registration attempts | 1. Attempt to register with same email 10+ times rapidly | System should block repeated attempts or show CAPTCHA | System allows unlimited registration attempts with no throttling | Major | High | Open | Tester
BUG_003 | TC_CHK_001 | Checkout | Order confirmation email not received | 1. Complete checkout as registered user 2. Check registered email inbox | Order confirmation email should arrive within 2 minutes | No email received after 10 minutes | Major | High | In Progress | Tester

## Test Summary Report
Test Summary Report – OpenCart Manual Testing
Project Name | OpenCart Demo
Version | 3.x
Tester Name | Md. Omar Khan
Test Environment | Windows 11 / Chrome
Test Start Date | 2026-03-03
Test End Date | 2026-03-03
Total Test Cases | 22
Passed | 20
Failed | 1
Blocked | 1
Pass % | ~95%
Overall Status | PASS
Module-wise Test Summary
Module | Total | Pass | Fail | Blocked | Pass %
User Registration | 4 | 4 | 0 | 0 | 100%
Login | 4 | 4 | 0 | 0 | 100%
Search | 3 | 3 | 0 | 0 | 100%
Shopping Cart | 4 | 3 | 0 | 1 | 75%
Checkout | 3 | 3 | 0 | 0 | 100%
Product Page | 3 | 2 | 1 | 0 | 67%
Navigation & UI | 3 | 3 | 0 | 0 | 100%